Plan of Work Discussion Questions

- Whom should we invite to be on the Task Force from each of the following groups?

  - Business Leaders

  - Development Professionals

  - Local Government

  - Educational Institutions

  - Other Community Leaders

- Which member of the Leadership Team will do each of the tasks shown in the Plan of Work? (Fill out the Plan of Work; see the Plan of Work template)

- What tasks will you assist other team members to complete? (Remember, each coordinator is only the leader of their primary area not the whole team.)

- Are there other tasks that need to be done which are not shown on the Plan of Work? If so, what are they, who should do them, and when should they be done?

- How many firms should be visited? (Remember that you need half as many volunteers as firms to be visited assuming each team visits four firms; two‐thirds as many if each team visits three firms and an equal number if each team visits two firms)

- What types of firms should we recommend be visited? (Manufacturing, tourism, retail, mixed sectors, dairy, etc.)?

- What do you think of the suggested agenda for the visitor training? Any changes needed?

- What date, time, and place should we hold the first Task Force meeting following visitor training

- What can we do to ensure a good turnout?

PLAN OF WORK TEMPLATE

Community ____________________________________________________________________________________

BR&E Coordinator: ___________________________ Phone: ________________Email: _______________________

Leadership Team Members assuming the following roles:

Coordinator: _______________________________	Phone: ______________	Email ____________________

Media Relations: ____________________________	Phone: ______________	Email ____________________

Business Resources: _________________________	Phone: ______________	Email ____________________

Milestone Mtg Facilitator: ____________________	Phone: ______________	Email ____________________

Visitation Director: __________________________	Phone: ______________	Email ____________________

Task Force Members:

Business Persons:

Development Professionals:

Local Government Officials:

Educational Professionals:

Other Community Leaders

Addresses: Attach complete addresses, with phone numbers and e‐mail for each person.

Preparations for the Visitor Training

If these preparations are done, the visitation completion rate will be very high, often above eighty percent. While the visitation director oversees this aspect of the program, all Leadership Team members and some Task Force members will need to help to get the tasks done on time.

Before the Firm Visits Are Done:

The Visitation Director coordinates this stage of the program but will need the help of all of the other members of

the Leadership Team.

Target Date/Person Responsible

Practice Visits

Select date 				__________________________________________________

Select two firms to visit 			__________________________________________________

Send firms copy of letter and survey 	__________________________________________________

Handle immediate follow‐up from visits 	__________________________________________________

Make copies of surveys from practice visits

and mail to the BR&E research office 	__________________________________________________

Find local economic development resources __________________________________________________

Task Force Organizational Meeting

Arrange room with speakerphone 		__________________________________________________

Who will personally contact whom? 	__________________________________________________

Mail out notices to Task Force 		__________________________________________________

Telephone tree reminder on meeting day 	__________________________________________________

Preparation for Visitor Training

Secure written endorsement from

sponsoring group 			_________________________________________________

Secure written endorsements from

other local groups 			_________________________________________________

Prepare mailing labels needed for program

1. Firms to be visited 		__________________________________________________

2. Firm Visitors 			__________________________________________________

3. Task Force members 		__________________________________________________

Mail notice of visitor training 		__________________________________________________

Organize telephone tree for contacting the

visitors on day of training 			__________________________________________________

Mail letter and survey to firms 		__________________________________________________

Arrange meeting room for training

(with phone jack and tables) 		__________________________________________________

Get speakerphone, DVR, TV and computer with

LCD projector 				__________________________________________________

Write a news release on BR&E Visitation 	__________________________________________________

Select date of first Task Force meeting

after firm visits are started for flag review 	__________________________________________________

Preparations for Media Coverage

The Media Coordinator either writes news releases for the local media or encourages media staff to cover the program at the following stages:

1. Applying for the program 		__________________________________________________

2. Being accepted in the program 	__________________________________________________

3. Training the visitors 		__________________________________________________

4. Visiting local businesses 		__________________________________________________

5. Follow up on industry concerns 	__________________________________________________

6. Special interest stories on unique

products/services of local firms 	__________________________________________________

7. Community Commencement Mtg 	__________________________________________________

8. Implement specific recommendations __________________________________________________

Preparations for Immediate Concerns or “Red flag” Review

The Business Resources leader organizes

this aspect of the program (often will call

on other Leadership Team members or

Task Force members for assistance).

Contact state/provincial, regional and/or

federal agencies on assistance available 	__________________________________________________

Prepare 1 to 2 page summary on assistance

Programs to send to firms after firm visits 	___________________________________________ _______

Organize 2 or 3 Task Force meetings for

red flag review, starting two weeks after

firm visits are started 			__________________________________________________

Coordinate red and yellow flag follow‐up 	__________________________________________________

Preparations for Task Force Retreat and Plan Recommendations and Plan Completion

The Leadership Team organizes this retreat under coordination of the Milestone Meeting Facilitator. This retreat is held about six to eight weeks after completing the surveys.

1. Make retreat physical arrangements	__________________________________________________

2. Send invitations for retreat 		__________________________________________________

3. Organize retreat notifications	__________________________________________________

Preparations for Community Input Commencement Meetings

The Milestone Meeting facilitator organizes the Leadership Team efforts on this meeting, which is held about four

weeks after the Retreat.

1. Make retreat physical arrangements	__________________________________________________

2. Send invitations for retreat 		__________________________________________________

3. Organize retreat notifications	__________________________________________________

Implementation of Priority Projects:

Date of First Task Force Meeting After

Community Commencement Meeting 	__________________________________________________